## Sheet1
Gantt Chart |  |  | PLANNED = |  | ACTUAL =
DATE
[7 empty] | START | [7 empty] | FINISH
| ACTIVITY | DESCRIPTION | PLANNED START | PLANNED DURATION | ACTUAL START | ACTUAL DURATION | 2014-11-17 | 2014-11-24 | 2014-12-01 | 2014-12-08 | 2014-12-15 | 2014-12-22 | 2014-12-29 | 2015-01-05 | 2015-01-09
IDEA GENERATION | [6 empty] | 2014-12-15: IDEA GENERATION
| 6-3-5 Idea Generation | A group of 6 has 5 minutes to generate as many solutions as possible about the problem area and then switches 3 times each | 2014-11-18 | 1 week | 2014-11-20 | 3 weeks | bar: 2014-11-17 to 2014-12-01
| Self Idea Generation | Using my URS and mood board I generated different ideas the the problem area and then noted them down | 2014-11-19 | 1 week | 2014-11-21 | 3 weeks | bar: 2014-11-17 to 2014-12-01
| 6 Hats Idea Generation | Ideas are generated around a the problem area, a group then critique these ideas using the 6 hats De Bono method | 2014-11-18 | 5 days | 2014-11-24 | 4 days | bar: 2014-11-17 to 2014-11-24
IDEA SHORTLISTING | [6 empty] | 2014-12-15: IDEA SHORTLISTING
| 6 Hats Idea Shortlisting | Ideas are generated around a the problem area, a group then critique these ideas using the 6 hats De Bono method | 2015-11-25 | 5 days | 2014-12-01 | 2 days | bar: 2014-11-24 to 2014-12-01
| NUF Test | This asses different solutions by asking are they a New idea, are they Useful and are they realistically feasible? | 2015-11-26 | 3 days | 2014-12-08 | 1 day | bar: 2014-11-24; 2014-12-08
| Weighted Pugh's Matirx | Using the URS generated with research, I compared each idea by giving them points on how well they met the URS | 2015-11-28 | 4 days | 2014-12-08 | 1 day | bar: 2014-11-24; 2014-12-08
| Weighted Matrix | Using the URS generated with research, I compared each idea by giving them points on how well they met the URS | 2015-11-29 | 4 days | 2014-12-08 | 1 day | bar: 2014-11-24; 2014-12-08
| Self Justified Shortlisting | This was simply gut feeling and talking to various people | 2014-12-01 | 1 day | 2014-12-08 | 1 week | bar: 2014-12-01 to 2014-12-08
IDEA DEVELOPMENT | [6 empty] | 2014-12-15: IDEA DEVELOPMENT
| Exploratory Sketches | These sketches begin to explore the chosen concepts and how the product could look | 2014-12-08 | 1 week | 2014-12-15 | 2 weeks | bar: 2014-12-08 to 2014-12-22
| Explanatory Sketches | These sketches start to look at form and starts to think about things such as materials that could be used | 2014-12-15 | 2 week | 2015-12-18 | 3 weeks | bar: 2014-12-15
| Persuasive Sketch | This is the 'money shot' of the product to show what it will look like | 2014-01-05 | 2 days | 2014-01-06 | 4 days | bar: 2015-01-05
MODEL BUILDING | [6 empty] | 2014-12-15: MODEL BUILDING
| Feasibility Test Plan | Feasibility Test Plans help to point out potential flaws/risks in the product and give you a goal for model making | 2014-12-22 | 3 days | 2014-12-29 | 1 week | bar: 2014-12-22 to 2014-12-29
| Model Build Plan | This helps to give model making structure | 2014-12-22 | 2 days | 2014-12-29 | 3 days | bar: 2014-12-22 to 2014-12-29
| Model Making | Model Making helps to give the concept a 3D presence and looks at potential problems it could face | 2014-12-29 | 1 week | 2014-12-29 | 1 week | bar: 2014-12-29
PRESENTING | [6 empty] | 2014-12-15: PRESENTING
| Presentation | Pitching the concept is very important | 2014-12-30 | 2 days | 2014-12-30 | 3 days | bar: 2014-12-29
| Digitial Portfolio | Presenting the final concept for assesment | 2015-01-05 | 2 days | 2015-01-05 | 4 days | bar: 2015-01-05