## Sheet1
Gantt Chart |  |  | PLANNED = |  | ACTUAL =
DATE
[7 empty] | START | [7 empty] | FINISH
| ACTIVITY | DESCRIPTION | PLANNED START | PLANNED DURATION | ACTUAL START | ACTUAL DURATION | 2015-01-27 | 2015-02-03 | 2015-02-10 | 2015-02-17 | 2015-02-24 | 2015-03-03 | 2015-03-10 | 2015-03-17 | 2015-03-24
PROTOTYPING | [6 empty] | 2015-02-24: IDEA GENERATION
| Works Like Prototyping | Produce sketches, CAD models and physical models of how the product could potentially work | 2015-02-10 | 3 weeks | 2015-03-03 | 3 weeks
| Looks Like Prototyping | Produce sketches, CAD models and physical models of how the product could potentially look | 2015-02-10 | 3 weeks | 2015-03-03 | 1 week
| CAD Modelling | Produce CAD models using dimensions and systems derived from prototyping | 2015-02-03 | 2 weeks | 2015-02-03 | 5 weeks
| Final Works Like Prototype | Final exhibtion works like model | 2015-03-10 | 1 week | 2015-03-17 | 1 week
| Final Looks Like Prototype | Final exhibtion looks like model | 2015-03-10 | 1 week | 2015-03-17 | 1 week
MANUFACTURING POSTER | [6 empty] | 2015-02-24: IDEA SHORTLISTING
| Planning/Layout | Setting out the layout and potential design of the manufacturing poster | 2015-01-27 | 1 day | 2015-02-10 | 2 days
| Market Research | Research into market size to estimate units per year, thus allowing a handful of manufacturing processes to look at | 2015-01-27 | 5 days | 2015-02-10 | 1 week
| Process and Material Research | Research into materials and manufacturing processes using the PRIMA sheet and select the most appropriate process and material | 2015-01-27 | 1 week | 2015-02-15 | 1 week
| DFMA | Make modifications and justify how the part has been designed for the process chosen | 2015-03-17 | 1 week | 2015-02-15 | 2 weeks
| Graphics and Presentation | Present data using infographics and other techniques | 2015-03-10 | 1 week | 2015-02-17 | 2 weeks
TECHNICAL DRAWINGS | [6 empty] | 2015-02-24: IDEA DEVELOPMENT
| Tolerance Research | Look into specific tolerances needed for the manufacturing process and wall thicknesses | 2015-03-17 | 2 days | 2015-02-24 | 3 days
| Standards Research | Look into standards that have to be followed for e.g. holes, diameters, fillets | 2015-03-17 | 2 days | 2015-02-24 | 5 days
| Layout | Plan layout of technical drawings | 2015-03-17 | 1 day | 2015-03-17 | 1 day
| Technical Drawings | Use solidworks files to generate technical drawings, adding dimensions, BOM and notes | 2015-03-20 | 5 days | 2015-02-24 | 3 days
| Checking/Approving | Get peers and colleagues to give feedback on technical drawings and make modifications | 2015-03-21 | 1 week | 2015-02-24 | 1 week
REVERSE ENGINEERING | [6 empty] | 2015-02-24: MODEL BUILDING
| Product Dismantle | Physically take apart reverse engineering product using tools, laying out systematically and taking pictures of each part | 2015-03-10 | 4 days | 2015-03-10 | 3 days
| Exhibition Stand Build | Design and build physical display stand for reverse engineered products | 2015-03-17 | 1 week | 2015-03-17 | 12 days
| Calculations/Measurements | Using equations and product components, calculate relevant statistics such as torque, power etc. | 2015-03-13 | 4 days | 2015-03-20 | 3 days
| Report/Leaflet | Present calculations and other necessary infromation about how the product works | 2015-03-19 | 4 days | 2015-03-21 | 2 days
PRESENTING AND PORTFOLIO | [6 empty] | 2015-02-24: PRESENTING
| Presentation | Plan what exhibition stand will look like | 2015-03-16 | 5 Days | 2015-03-20 | 3 Days
| Digitial Portfolio | Design and build online portfolio to present work | 2015-03-16 | 5 Days | 2015-03-20 | 3 Days
| Presentation Speaches | Plan, write, practice and record presentation speaches for manufacturing and reverse engineering | 2015-03-16 | 5 Days | 2015-03-20 | 3 Days